CONDUIT CONTROL CENTER

Product & Work Breakdown Structure

v0.1 MVP Implementation Plan

May 31, 2026 Based on SRS v1.1 Total Estimate: 41–52 days

Raspberry Pi 4  ·  Ubuntu 22.04 ARM64  ·  MIT Licence

# 1. Introduction

This document defines the Product Breakdown Structure (PBS) and Work Breakdown Structure (WBS) for the Conduit Control Center v0.1 MVP. It translates the requirements in SRS v1.1 Section 3 into deliverable components and actionable tasks with effort estimates and dependencies.

## 1.1 How to Read This Document

- The PBS (Section 2) defines what the product is made of — components and deliverables.

- The WBS (Section 3) defines the work needed to build those components — tasks with estimates.

- Section 4 maps WBS tasks to GitHub Issues.

- Effort estimates are in developer-days (one day = 6–7 focused hours). Ranges reflect uncertainty.

- Dependencies show which tasks must be completed before a task can begin.

## 1.2 Effort Summary

| ID | Epic | Tasks | Min Days | Max Days |
| --- | --- | --- | --- | --- |
| E1 | Project Setup & Repository | 5 | 3 | 4 |
| E2 | Infrastructure & Deployment | 7 | 8 | 10 |
| E3 | Backend — Authentication | 5 | 4 | 5 |
| E4 | Backend — Conduit Adapter | 4 | 4 | 5 |
| E5 | Backend — Metrics & Logs | 4 | 4 | 5 |
| E6 | Frontend | 8 | 8 | 10 |
| E7 | Security Hardening | 4 | 3 | 4 |
| E8 | Testing | 3 | 4 | 5 |
| E9 | Documentation | 3 | 4 | 3 |
| TOTAL | 9 Epics, 43 Tasks | 43 | 40 | 50 |

⚠ Estimates assume a single developer working alone. A two-person team can parallelize E3–E6 and reduce total elapsed time to roughly 4–5 weeks.

# 2. Product Breakdown Structure (PBS)

The PBS shows what the product is made of. Each node is a concrete deliverable that can be tested and verified independently.

ℹ Conduit Control Center v0.1 is composed of 9 product components. The tree below shows how they relate.

| L | Code | Deliverable / Component |
| --- | --- | --- |
| 0 | CCC v0.1 | Conduit Control Center — complete MVP release |
| 1 | P1 — Repository | Version-controlled source code, CI pipeline, issue templates |
|  | P1.1 | GitHub repository with branch protection and CI/CD configured |
|  | P1.2 | GitHub Actions workflow (lint, test, security audit) |
|  | P1.3 | Issue and pull request templates |
|  | P1.4 | Development environment documentation |
| 1 | P2 — Infrastructure | Server-side deployment artefacts that host the application |
|  | P2.1 | install.sh — automated installation script for Ubuntu 22.04 ARM64 |
|  | P2.2 | uninstall.sh — clean removal script |
|  | P2.3 | conduit-cc.service — systemd service unit |
|  | P2.4 | conduit-cc.conf — Nginx virtual host with HTTPS |
|  | P2.5 | TLS certificate (Cloudflare Origin Cert or Let's Encrypt) |
|  | P2.6 | UFW firewall rules (ports 22, 80, 443 only) |
|  | P2.7 | cloudflare-ddns.sh — DDNS update script; cron job entry; ddns.log output file |
| 1 | P3 — Backend API | FastAPI application serving authenticated REST endpoints |
|  | P3.1 | Application skeleton (FastAPI app, config loader, .env support) |
|  | P3.2 | Authentication module (login, logout, session, lockout) |
|  | P3.3 | Settings module (change password, session timeout config) |
|  | P3.4 | Conduit adapter module (status, start, stop, restart, pairing) |
|  | P3.5 | Metrics module (system health, traffic counters) |
|  | P3.6 | Logs module (last N lines of Conduit log, redaction) |
|  | P3.7 | Health check endpoint GET /api/health |
|  | P3.8 | Security middleware (CSRF, rate limiting, security headers) |
|  | P3.9 | Input validation schemas (Pydantic models) |
|  | P3.10 | DDNS status endpoint GET /api/ddns/status (reads ddns.log) |
| 1 | P4 — Frontend | Single-page web dashboard (HTML/CSS/Vanilla JS, no build step) |
|  | P4.1 | Login page (login.html) |
|  | P4.2 | Dashboard layout and navigation (dashboard.html + base CSS) |
|  | P4.3 | Node status and control panel (status widget + start/stop/restart buttons) |
|  | P4.4 | System health panel (CPU, RAM, temp, disk) |
|  | P4.5 | Traffic counter widget |
|  | P4.6 | Log viewer panel (last 200 lines, manual refresh) |
|  | P4.7 | Settings page (change password, session timeout) |
|  | P4.8 | JavaScript polling module (status, metrics every 5–10 s) |
|  | P4.9 | DDNS status panel (current IP, last update time, last result) |
| 1 | P5 — Configuration | Runtime configuration files and secret templates |
|  | P5.1 | .env.example — secret placeholders including CF_API_TOKEN, CF_ZONE_NAME, CF_RECORD_NAME, SESSION_SECRET |
|  | P5.2 | config.example.json — application configuration template |
|  | P5.3 | SQLite schema for sessions and metrics |
| 1 | P6 — Test Suite | Automated tests providing ≥60% backend coverage |
|  | P6.1 | Unit tests for backend modules (pytest) |
|  | P6.2 | Integration tests for API endpoints (pytest + httpx) |
|  | P6.3 | Install script syntax check (bash -n) |
| 1 | P7 — Documentation | Written materials needed for a public open-source release |
|  | P7.1 | README.md — project description, install instructions, screenshot placeholder |
|  | P7.2 | CONTRIBUTING.md — dev setup, coding standards, PR process |
|  | P7.3 | CHANGELOG.md — v0.1.0 entry |
|  | P7.4 | SECURITY.md — vulnerability disclosure policy |
|  | P7.5 | CODE_OF_CONDUCT.md — Contributor Covenant v2.1 |

# 3. Work Breakdown Structure (WBS)

The WBS lists every task needed to produce the PBS deliverables. Tasks are grouped by epic (E1–E9). Each task has an effort estimate in developer-days and a list of prerequisite tasks.

ℹ D = developer-days. 1 D = approximately 6–7 focused hours. Ranges (e.g. 0.5–1) reflect uncertainty.

| ID | Task | Effort | Depends on |
| --- | --- | --- | --- |
| E1 | Project Setup & Repository | 3–4 D | — |
| 1.1 | Create GitHub repository; configure branch protection on main and develop; add .gitignore, .gitattributes | 0.5 D | — |
| 1.2 | Create GitHub Actions workflow: lint (ruff), test (pytest), security audit (pip-audit), install script syntax check | 1 D | 1.1 |
| 1.3 | Add GitHub issue templates (Bug Report, Feature Request, Security Vulnerability) and PR template | 0.5 D | 1.1 |
| 1.4 | Define repository structure; create all top-level directories and placeholder files | 0.5 D | 1.1 |
| 1.5 | Write developer environment setup guide (local Python venv, how to run tests, how to run the dev server) | 0.5–1 D | 1.4 |
| E2 | Infrastructure & Deployment | 6–8 D | — |
| 2.1 | Write conduit-cc.service systemd unit (run as conduit-cc user, sandboxing, restart policy) | 0.5 D | 1.4 |
| 2.2 | Write conduit-cc.conf Nginx virtual host (proxy_pass to 127.0.0.1:8000, security headers, login rate limit). Configure ngx_http_realip_module: real_ip_header CF-Connecting-IP; set_real_ip_from for all Cloudflare IP ranges. HTTP→HTTPS only needed for direct-IP path; Cloudflare handles browser TLS. | 1.5 D | 1.4 |
| 2.3 | Write docs/pre-install.md (user-facing pre-install checklist: Cloudflare dashboard steps, Origin Cert creation, API token scoping) and docs/tls-setup.md (Cloudflare Origin Cert + nginx config; Let's Encrypt alternative path for direct-IP) | 1.5 D | 2.2 |
| 2.4 | Write install.sh: [interactive] prompt for CF_API_TOKEN → validate via Cloudflare API (zone lookup); prompt for CF_ZONE_NAME + CF_RECORD_NAME → validate DNS A record exists + proxied:true; prompt for Origin Cert + key paths → validate with openssl; prompt for admin password; write /etc/conduit-cc/.env (640, conduit-cc); configure Nginx server_name from CF_RECORD_NAME; idempotent; post-install summary with dashboard URL | 3–4 D | 2.1, 2.2, 2.3 |
| 2.5 | Write uninstall.sh (reverse of install.sh; confirm before deleting config) | 0.5 D | 2.4 |
| 2.6 | Write update.sh (stop service, backup config, pull latest, reinstall deps, run migrations, restart) | 1 D | 2.4 |
| 2.7 | Integrate cloudflare-ddns.sh using Script B behaviour (preserve proxy status from API, never force override): read CF_* vars from .env; structured JSON log per run; install.sh runs script once immediately after cron setup to verify end-to-end API → DNS update works before completing; add CF_API_TOKEN / CF_ZONE_NAME / CF_RECORD_NAME to .env.example with comments; logrotate config for ddns.log | 0.5 D | 2.4 |
| E3 | Backend — Authentication | 4–5 D | — |
| 3.1 | Create FastAPI application skeleton: app factory, config loader, .env support (python-dotenv), CORS, error handlers | 1 D | 1.4 |
| 3.2 | Implement session store: SQLite table; create/validate/expire/destroy session; cryptographically random session ID (32 bytes) | 1 D | 3.1 |
| 3.3 | Implement auth endpoints: POST /api/auth/login (bcrypt verify, set session cookie), POST /api/auth/logout (destroy session) | 1 D | 3.2 |
| 3.4 | Implement account lockout: track failed attempts per username; lock for 15 min after 5 failures; ccc-unlock CLI command | 0.5–1 D | 3.3 |
| 3.5 | Implement session middleware: validate session cookie on every protected route; redirect unauthenticated requests to /login | 0.5 D | 3.2 |
| E4 | Backend — Conduit Adapter | 4–5 D | — |
| 4.1 | Implement Conduit adapter: call systemd (start/stop/restart/status) via subprocess + systemctl; parse output into structured status | 1.5 D | 3.1 |
| 4.2 | Implement GET /api/status endpoint: return node status + last-changed timestamp + current systemd state | 0.5 D | 4.1 |
| 4.3 | Implement POST /api/conduit/{start¦stop¦restart} endpoints: validate action; call adapter; return new status | 0.5 D | 4.1 |
| 4.4 | Implement pairing workflow endpoint: accept pairing link transiently; pass to Conduit CLI; never log or store the link; return result | 1.5–2 D | 4.1 |
| E5 | Backend — Metrics & Logs | 3–4 D | — |
| 5.1 | Implement GET /api/metrics/system: read CPU %, RAM MB/%, CPU temp (°C), disk usage GB/%; use psutil; cache for 5 s | 1 D | 3.1 |
| 5.2 | Implement GET /api/metrics/traffic: read bytes transferred from Conduit log or metrics file; return upload + download totals | 1 D | 3.1 |
| 5.3 | Implement GET /api/logs: read last N lines of Conduit service log (journalctl or log file); redact pairing link patterns; return JSON array | 1–2 D | 3.1 |
| 5.4 | Implement GET /api/ddns/status: parse last 50 lines of /var/log/conduit-cc/ddns.log; extract last update timestamp, public IP, and success/failure; return JSON | 0.5–1 D | 3.1 |
| E6 | Frontend | 7–9 D | — |
| 6.1 | Create base layout: base.css (typography, colour variables, responsive grid), base.js (fetch wrapper, error toast) | 1 D | 3.1 |
| 6.2 | Build login page (login.html + login.js): form, validation, error display, redirect on success | 0.5–1 D | 6.1 |
| 6.3 | Build dashboard shell (dashboard.html): navigation sidebar, page header, content area, logout button | 1 D | 6.1 |
| 6.4 | Build node status & control panel: status badge (colour-coded), Start/Stop/Restart buttons with confirmation dialog and spinner | 1–1.5 D | 6.3, 4.2, 4.3 |
| 6.5 | Build system health panel: CPU, RAM, temp, disk gauges; polling every 10 s via setInterval; colour-coded thresholds | 1–1.5 D | 6.3, 5.1 |
| 6.6 | Build traffic counter widget: upload + download totals; polling every 30 s | 0.5 D | 6.3, 5.2 |
| 6.7 | Build log viewer panel: display last 200 lines; manual refresh button; auto-refresh every 30 s | 1 D | 6.3, 5.3 |
| 6.8 | Build settings page: change password form (current + new + confirm); session timeout selector; save with success/error feedback | 1–1.5 D | 6.3 |
| 6.9 | Build DDNS status panel: show current public IP, hostname (CF_RECORD_NAME), last update time, last result badge (green/red); polls GET /api/ddns/status every 60 s | 0.5 D | 6.3, 5.4 |
| E7 | Security Hardening | 3–4 D | — |
| 7.1 | Add Nginx security headers to conduit-cc.conf: Content-Security-Policy, X-Frame-Options, X-Content-Type-Options, Referrer-Policy, HSTS | 0.5 D | 2.2 |
| 7.2 | Add CSRF protection to all state-changing API endpoints (double-submit cookie pattern) | 1 D | 3.5 |
| 7.3 | Add Nginx rate limiting for POST /api/auth/login: 10 req/s per IP; return 429 with Retry-After header | 0.5 D | 2.2 |
| 7.4 | Audit all API inputs for Pydantic model coverage; ensure no raw request data reaches adapter or filesystem | 1–2 D | 4.1, 5.1, 5.2, 5.3 |
| E8 | Testing | 4–5 D | — |
| 8.1 | Write unit tests for backend modules: auth (login, lockout, session expiry), adapter (status parsing), metrics (psutil mock), logs (redaction) | 2 D | 3.3, 3.4, 4.1, 5.1, 5.3 |
| 8.2 | Write integration tests for all v0.1 API endpoints using pytest + httpx test client | 1.5 D | 8.1 |
| 8.3 | Run install.sh on a fresh Ubuntu 22.04 ARM64 image (Raspberry Pi 4 or VM); document and fix any failures | 0.5–1 D | 2.4 |
| E9 | Documentation | 3–4 D | — |
| 9.1 | Write README.md: project description, feature list, install instructions, screenshot placeholder, licence and CI badges, link to CONTRIBUTING | 1–1.5 D | 2.4 |
| 9.2 | Write CONTRIBUTING.md: dev setup, how to run tests, commit message format (Conventional Commits), PR checklist | 0.5–1 D | 1.4 |
| 9.3 | Write SECURITY.md (disclosure email, response SLA) and CODE_OF_CONDUCT.md (Contributor Covenant v2.1) | 0.5 D | 1.4 |
| 9.4 | Write CHANGELOG.md v0.1.0 entry: list every implemented feature and known limitation | 0.5 D | 8.3 |

# 4. Critical Path

The critical path is the longest chain of dependent tasks. Delays on this path delay the entire v0.1 release.

ℹ Critical path (single developer): 1.1 → 1.4 → 3.1 → 3.2 → 3.3 → 4.1 → 4.4 → 6.1 → 6.3 → 6.4 → 8.1 → 8.2 → 8.3 → 9.1 → 9.4

| Phase | Critical Path Task | Effort |
| --- | --- | --- |
| Phase 1 | 1.1 Create repository and branch protection | 0.5 D |
| Phase 1 | 1.4 Define repository structure | 0.5 D |
| Phase 2 | 3.1 FastAPI application skeleton | 1 D |
| Phase 2 | 3.2 Session store (SQLite) | 1 D |
| Phase 2 | 3.3 Auth endpoints (login/logout) | 1 D |
| Phase 2 | 4.1 Conduit adapter (systemctl wrapper) | 1.5 D |
| Phase 2 | 4.4 Pairing workflow endpoint | 1.5–2 D |
| Phase 3 | 6.1 Base layout CSS + JS | 1 D |
| Phase 3 | 6.3 Dashboard shell | 1 D |
| Phase 3 | 6.4 Node status & control panel | 1–1.5 D |
| Phase 4 | 8.1 Unit tests | 2 D |
| Phase 4 | 8.2 Integration tests | 1.5 D |
| Phase 4 | 8.3 Test install.sh on real hardware | 0.5–1 D |
| Phase 4 | 9.1 README.md | 1–1.5 D |
| Phase 4 | 9.4 CHANGELOG.md v0.1.0 | 0.5 D |

## 4.1 Parallelisation Opportunities

If two or more developers work simultaneously, the following task groups can be parallelised after Phase 1 is complete:

| After | Developer A | Developer B |
| --- | --- | --- |
| Phase 1 done | E3 (Auth) + E4 (Adapter) | E2 (Infrastructure) |
| E3 done | E6 (Frontend) | E5 (Metrics & Logs) + E7 (Security) |
| E4–E6 done | E8 (Testing) | E9 (Documentation) |

✓ With two developers and parallelisation, v0.1 is achievable in 4–5 weeks elapsed time.

# 5. GitHub Issue Mapping

Each WBS task maps to one GitHub Issue. The table below shows the mapping, suggested labels, and milestone.

| WBS | Issue | Title | Labels | Effort |
| --- | --- | --- | --- | --- |
| 1.1 | #1 | Initialize repository structure and branch protection | setup | 0.5 D |
| 1.2 | #2 | Create GitHub Actions CI pipeline | setup, ci | 1 D |
| 1.3 | #3 | Add issue templates and PR template | setup, docs | 0.5 D |
| 1.4 | #4 | Define repository directory structure | setup | 0.5 D |
| 1.5 | #5 | Write developer environment setup guide | docs | 0.5 D |
| 2.1 | #6 | Create systemd service unit (conduit-cc.service) | infrastructure | 0.5 D |
| 2.2 | #7 | Create Nginx virtual host configuration | infrastructure | 1 D |
| 2.3 | #8 | Write TLS setup guides (Cloudflare + Let's Encrypt) | infrastructure, docs | 1 D |
| 2.4 | #9 | Write install.sh installation script | infrastructure | 2–3 D |
| 2.5 | #10 | Write uninstall.sh removal script | infrastructure | 0.5 D |
| 2.6 | #11 | Write update.sh upgrade script | infrastructure | 1 D |
| 3.1 | #12 | Create FastAPI application skeleton | backend | 1 D |
| 3.2 | #13 | Implement SQLite session store | backend, auth | 1 D |
| 3.3 | #14 | Implement login and logout endpoints | backend, auth | 1 D |
| 3.4 | #15 | Implement account lockout and ccc-unlock CLI | backend, auth, security | 1 D |
| 3.5 | #16 | Implement session validation middleware | backend, auth | 0.5 D |
| 4.1 | #17 | Implement Conduit adapter (systemctl wrapper) | backend, conduit | 1.5 D |
| 4.2 | #18 | Implement GET /api/status endpoint | backend, conduit | 0.5 D |
| 4.3 | #19 | Implement start/stop/restart endpoints | backend, conduit | 0.5 D |
| 4.4 | #20 | Implement pairing workflow (transient, no storage) | backend, conduit, security | 1.5 D |
| 5.1 | #21 | Implement GET /api/metrics/system | backend, metrics | 1 D |
| 5.2 | #22 | Implement GET /api/metrics/traffic | backend, metrics | 1 D |
| 5.3 | #23 | Implement GET /api/logs with redaction | backend, logs | 1 D |
| 6.1 | #24 | Build base CSS layout and JS fetch wrapper | frontend | 1 D |
| 6.2 | #25 | Build login page | frontend, auth | 0.5 D |
| 6.3 | #26 | Build dashboard shell and navigation | frontend | 1 D |
| 6.4 | #27 | Build node status and control panel | frontend, conduit | 1 D |
| 6.5 | #28 | Build system health panel | frontend, metrics | 1 D |
| 6.6 | #29 | Build traffic counter widget | frontend, metrics | 0.5 D |
| 6.7 | #30 | Build log viewer panel | frontend, logs | 1 D |
| 6.8 | #31 | Build settings page (change password) | frontend, auth | 1 D |
| 7.1 | #32 | Add security headers to Nginx config | security, infrastructure | 0.5 D |
| 7.2 | #33 | Implement CSRF protection | security, backend | 1 D |
| 7.3 | #34 | Add login rate limiting in Nginx | security, infrastructure | 0.5 D |
| 7.4 | #35 | Audit Pydantic model coverage for all inputs | security, backend | 1 D |
| 8.1 | #36 | Write backend unit tests (≥60% coverage) | testing | 2 D |
| 8.2 | #37 | Write API integration tests | testing | 1.5 D |
| 8.3 | #38 | Test install.sh on Raspberry Pi 4 hardware | testing, infrastructure | 1 D |
| 9.1 | #39 | Write README.md | docs | 1 D |
| 2.7 | #41 | Integrate Cloudflare DDNS script and cron job | infrastructure, security | 0.5 D |
| 5.4 | #42 | Implement GET /api/ddns/status endpoint | backend, metrics | 0.5 D |
| 6.9 | #43 | Build DDNS status panel on dashboard | frontend, metrics | 0.5 D |
| 9.2–9.3 | #40 | Write CONTRIBUTING.md, SECURITY.md, CODE_OF_CONDUCT.md | docs | 1 D |

END OF DOCUMENT